## PERT-COST INPUT
CURRENT DATE = | [5 empty] | IMMEDIATE | [6 empty] | 0
[6 empty] | PREDECESSORS | [5 empty] | 0 | 20
WORK PACKAGE | NODE | BUDGETED TIME | BUDGETED COST | PERCENT COMPLETE | COST TO DATE | NODE | PREDECESSOR |  |  | Name | Marginal Cost | ES | EF | VSTART | VFINISH | m
AA | A | 4 | 2000 |  |  |  |  | 1 | A | A | 500 | 0 | 4 | 0 | 0 | 4
BB | B | 6 | 3000 |  |  |  |  | 2 | B | B | 500 | 0 | 6 | 0 | 0 | 6
CC | C | 5 | 4500 |  |  |  |  | 3 | C | C | 900 | 0 | 5 | 0 | 0 | 5
DD | D | 6 | 2500 |  |  |  |  | 4 | D | D | 416.6667 | 0 | 6 | 0 | 0 | 6
EE | E | 2 | 500 |  |  |  |  | 5 | E | E | 250 | 0 | 2 | 0 | 0 | 2
FF | F | 13 | 13000 |  |  |  |  | 6 | F | F | 1000 | 0 | 13 | 0 | 0 | 13
GG | G | 1 | 1500 |  |  |  |  | 7 | G | G | 1500 | 0 | 1 | 0 | 0 | 1
HH | H | 20 | 6000 |  |  |  |  | 8 | H | H | 300 | 0 | 20 | 0 | 0 | 20
II | I | 9 | 7000 |  |  |  |  | 9 | I | I | 777.7778 | 0 | 9 | 0 | 0 | 9
[8 empty] | 10 | J |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 11 | K |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 12 | L |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 13 | M |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 14 | N |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 15 | O |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 16 | P |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 17 | Q |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 18 | R |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 19 | S |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 20 | T |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 21 | U |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 22 | V |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 23 | W |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 24 | X |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 25 | Y |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 26 | Z |  | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
Note on A55: Copyright 2001 John Lawrence & Barry Pasternack

## PERT-COST OUTPUT
PERT/COST ANALYSIS | [12 empty] | OBJ FCTN | 0
DATE OF ANALYSIS |  |  |  | 0 | TOTAL PROJECT BUDGET |  |  | 40000 |  |  |  |  | PRJ TIME | 20
EXPECTED COMPLETION TIME |  |  |  | 20 | COST OF WORK TO DATE |  |  | 0 |  | Activity | Pred | PROJ ACT | ES | EF | V ST | VFIN | TIME
EXPECTED REMAINING TIME |  |  |  |  | VALUE OF WORK TO DATE |  |  | 0 | A |  |  | A | 0 | 4 | 0 | 0 | 4
EXPECTED PROJECT DELAY |  |  |  |  | COST OVERRUN |  |  | 0 | B |  |  | B | 0 | 6 | 0 | 0 | 6
[9 empty] | C |  |  | C | 0 | 5 | 0 | 0 | 5
|  | BUDGETED VALUES |  | TO DATE VALUES |  |  | ANALYSIS TO DATE |  | D |  |  | D | 0 | 6 | 0 | 0 | 6
WORK PACKAGE | NODE | TOTAL TIME | TOTAL COST | PERCENT COMPLETE | VALUE TO DATE | COST TO DATE | COST OVERRUN | TIME REMAINING | E |  |  | E | 0 | 2 | 0 | 0 | 2
AA | A | 4 | 2000 | 0 | 0 | 0 | 0 | 4 | F |  |  | F | 0 | 13 | 0 | 0 | 13
BB | B | 6 | 3000 | 0 | 0 | 0 | 0 | 6 | G |  |  | G | 0 | 1 | 0 | 0 | 1
CC | C | 5 | 4500 | 0 | 0 | 0 | 0 | 5 | H |  |  | H | 0 | 20 | 0 | 0 | 20
DD | D | 6 | 2500 | 0 | 0 | 0 | 0 | 6 | I |  |  | I | 0 | 9 | 0 | 0 | 9
EE | E | 2 | 500 | 0 | 0 | 0 | 0 | 2 | J |  |  |  | 0 | 0 | 0 | 0 | 0
FF | F | 13 | 13000 | 0 | 0 | 0 | 0 | 13 | K |  |  |  | 0 | 0 | 0 | 0 | 0
GG | G | 1 | 1500 | 0 | 0 | 0 | 0 | 1 | L |  |  |  | 0 | 0 | 0 | 0 | 0
HH | H | 20 | 6000 | 0 | 0 | 0 | 0 | 20 | M |  |  |  | 0 | 0 | 0 | 0 | 0
II | I | 9 | 7000 | 0 | 0 | 0 | 0 | 9 | N |  |  |  | 0 | 0 | 0 | 0 | 0
[9 empty] | O |  |  |  | 0 | 0 | 0 | 0 | 0
[9 empty] | P |  |  |  | 0 | 0 | 0 | 0 | 0
[9 empty] | Q |  |  |  | 0 | 0 | 0 | 0 | 0
[9 empty] | R |  |  |  | 0 | 0 | 0 | 0 | 0
[9 empty] | S |  |  |  | 0 | 0 | 0 | 0 | 0
[9 empty] | T |  |  |  | 0 | 0 | 0 | 0 | 0
[9 empty] | U |  |  |  | 0 | 0 | 0 | 0 | 0
[9 empty] | V |  |  |  | 0 | 0 | 0 | 0 | 0
[9 empty] | W |  |  |  | 0 | 0 | 0 | 0 | 0
[9 empty] | X |  |  |  | 0 | 0 | 0 | 0 | 0
[9 empty] | Y |  |  |  | 0 | 0 | 0 | 0 | 0
[9 empty] | Z |  |  |  | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 |  | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0